## Framework
STAKEHOLDER | RACI | POWER/INFLUENCE | URGENCY | INTEREST | RISK/REWARD | CURRENT STATUS | TIER | INFLUENCES | INFLUENCED BY
name / position | Responsible (doer) Accountable (final decision-maker/owner) Consulted (subject matter advisor) Informed (kept in the loop) | Scale: 1-5 (1 = low, 5 = high) | Scale: 1-5 (1 = low, 5 = high) | Scale: 1-5 (1 = low, 5 = high) | RISK: What they fear REWARD: What they gain | Champion Indifferent Skeptical Blocking | Core Satellite | name1; name2;... | name1; name2;...

## Framework Example
STAKEHOLDER | RACI | POWER/INFLUENCE | URGENCY | INTEREST | RISK/REWARD | CURRENT STATUS | TIER | INFLUENCES | INFLUENCED BY
Sarah C (VP Product) | Accountable | 5 | 5 | 4 | Risk: Delay; Reward: Market lead | Champion | Core | Elena R (PM)
Marcus V (Lead Arch) | Responsible | 4 | 5 | 3 | Risk: Tech debt; Reward: Scalability | Champion | Core | Elena R (PM) | Maria C (CFO)
Elena R (PM) | Responsible | 3 | 5 | 2 | Risk: Scope creep; Reward: On-time delivery | Indifferent | Satellite | Marcus V (Lead Arch) | Maria C (CFO)
David K (Eng Dir) | Consulted | 2 | 5 | 1 | Risk: Resource drain; Reward: Tech adoption | Champion | Satellite | Marcus V (Lead Arch) | Maria C (CFO)
Legal Counsel | Consulted | 2 | 5 | 1 | Risk: Compliance breach; Reward: Risk mitigation | Blocking | Core |  | Marcus V (Lead Arch)
Procurement Head | Informed | 1 | 4 | 1 | Risk: Budget overrun; Reward: Cost efficiency | Indifferent | Core |  | Marcus V (Lead Arch)
Cloud Vendor | Informed | 5 | 1 | 5 | Risk: Churn; Reward: Contract renewal | Indifferent | Satellite |  | Elena R (PM)
Maria C (CFO) | Accountable | 5 | 4 | 5 | Risk: budget overrun; Reward: cost savings | Champion | Core | Sam P (VP Eng);Jordan L (PM) | Marcus V (Lead Arch)
Sam P (VP Eng) | Responsible | 4 | 3 | 4 | Risk: timeline slip; Reward: promotion | Indifferent | Core | Jordan L (PM) | Maria C (CFO); Elena R (PM)
Jordan L (PM) | Responsible | 3 | 5 | 3 | Risk: scope creep; Reward: shipped feature | Skeptical | Core | Marcus V (Lead Arch) | Maria C (CFO);Sam P (VP Eng)
Alex R (Legal) | Consulted | 2 | 2 | 2 | Risk: compliance exposure; Reward: none | Blocking | Satellite | Sarah C (VP Product) | Maria C (CFO)
Priya N (Client Sponsor) | Informed | 4 | 3 | 5 | Risk: vendor delay; Reward: on-time launch | Champion | Satellite | Maria C (CFO) | Maria C (CFO); Sarah C (VP Product)

## Info Gathering
QUESTIONS TO ASK
Who will experience direct or secondary ripple effects from this?
Who gains from this?
Who loses from this?
Who will inherit this? (maintenance, support, cleanup, etc.)
Who is the gatekeeper or mentor for each person involved in this decision/project?
ROLES TO CHECK
Project & Core Execution:
Direct delivery team | FALSE
Contractors | FALSE
Project sponsor | FALSE
Internal Enablers & Governance:
Legal | FALSE
InfoSec | FALSE
Compliance | FALSE
Procurement | FALSE
HR | FALSE
IT Architecture | FALSE
Downstream Operations:
Frontline staff | FALSE
Tier-1 support | FALSE
Systems maintenance | FALSE
Facilities | FALSE
Customers & End Users:
Direct product users | FALSE
Client-side administrators | FALSE
Internal employee users | FALSE
Supply Chain & Partners:
Upstream component vendors | FALSE
Integration partners | FALSE
External logistics | FALSE
Capital & Oversight:
Investors | FALSE
Board members | FALSE
Executive audit committees | FALSE
Consultants/Experts | FALSE
External Institutional Bodies:
Regulators | FALSE
Industry standards boards | FALSE
Municipal authorities | FALSE
Community & Public Interest:
Local neighborhood groups | FALSE
Advocacy organizations | FALSE
ESG/environmental compliance officers | FALSE
Environment (nautre/physical) | FALSE
Market Environment:
Competitors | FALSE
Trade associations | FALSE
Industry analysts | FALSE